## 1. COVID-19 Risk Assessment
COVID-19 Risk Assesment Matrix
KEY
RISK SEVERITY |  | RISK LIKELIHOOD
Acceptable (Little to no effect on event) |  | Improbable (Risk is unlikely to occur)
Undesirable (Serious impact to the course of action and outcome) |  | Possible (Risk is fairly likely to occur)
Intolerable (Could result in disaster) |  | Probable (Risk is highly likely to occur)
RISK ID | IDENTIFIED RISK | ASSIGNED TO | WORKSTREAM | CONSEQUENCE | RISK SEVERITY | RISK LIKELIHOOD | RISK RATING CALCULATION (autopopulates results) | ACTION (auto-populates results) | ACTIONS REQUIRED
RISK-1001 | The risk that we do not have the technology in place to support remote workng | Head of IT | IT | The consequence of this risk could be that we are unable to operate the business in a remote working situation if the office is forced to close. | Intolerable | Possible | High | Implment risk response actions
RISK-1002 | The risk that we do not communicate the latest and approprate guidance to staff | CMT Lead | CMT | The consequence of this risk could lead to the health and wellbeing of an employee being impacted due to a lack of awareness on the latest COVID-19 guidance | Intolerable | Improbable | Medium | Monitor and develop risk response
RISK-1003 |  |  |  |  | Acceptable | Probable | Medium | Monitor and develop risk response
[5 empty] | Undesirable | Improbable | Medium | Monitor and develop risk response
[5 empty] | Undesirable | Possible | Medium | Monitor and develop risk response
[5 empty] | Undesirable | Probable | Medium | Monitor and develop risk response
[5 empty] | Intolerable | Improbable | Medium | Monitor and develop risk response
[5 empty] | Intolerable | Possible | High | Implment risk response actions
[5 empty] | Intolerable | Probable | High | Implment risk response actions

## 2. COVID-19 Comms Tracker
COVID-19 Communication Tracker
SUBJECT | DATE OF COMMUNICATION | STATUS | COMMUNICATION METHOD | RECIPIENTS | AUTHOR | APPROVAL REQUIRED | SENDER
Internal Communications
! Important: Employee Guidance on 2019 Novel Coronavirus | 2020-02-03 | Not Started | Email | All Employees
! Important: Updated Guidance on Coronavirus COVID-19 | 2020-02-25 | In progress | Email | All Employees
! Important: Coronavirus preparedness and response | 2020-03-02 | Complete | Email | All Employees
Reception Signage | 2020-03-03 | In progress | Email | All Office Locations
Intranet page created | 2020-03-03 | In progress | Intranet | All Employees
External Communications
LinkedIn Post | 2020-03-05 | In progress | Email | Public
Email update to all clients | 2020-03-05 | Complete | Email | All Clients
Facebook Post | 2020-03-05 | In progress | Email | Public
Please note the above are illustrative examples to be removed / updated as appropriate to your organisation

## 3. COVID-19 Response Plan
COVID-19 Response Plan
PRIORITY | RELATED RISK IDs | TASK NAME | DUE DATE | OWNER | STATUS | WORKSTREAM | NOTES
Communication Response Actions
Medium |  | Send out initial internal communications | 2020-03-20 |  | At Risk | HR
Medium |  | Draft external communications for review | 2020-03-20 |  | Not Started
Risk Response Actions
High | RISK-1001 | Team Isolation Impact analysis | 2020-03-20 |  | Complete
High |  | Work From Home Systems Training | 2020-03-20 |  | Overdue
Please note the above are illustrative examples to be removed / updated as appropriate to your organisation
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Would make this ' owner'
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this be % complete or simple status i.e. `overdue, not started, in progress, at risk, complete, N/A etc) Reply: @Dominic Ash Agree - @Matthew Coleman can you please update to 'not started' 'in progress' 'overdue' 'complete'

## Data List
Data Lists
Risk Assessment Matrix - 'Column E'. Response Plan - 'Column I' | Comms Tracker - 'Column C' | Comms Tracker - 'Column D' | Response Plan - 'Column G' | Response Plan - 'Column A'
Workstream - 'Column E' and Workstream - 'Column I' | Status - 'Column C' | Communication Method - 'Column D' | Status - 'Column G' | Priority - 'Column A'
IT | Not Started | Email | Not Started | High
HR | In progress | Face to Face | In Progress | Medium
Finance | Complete | Telephone | Complete | Low
Operations | Recurring Weekly | Video Conference | At Risk
Compliance | Recurring Monthly | Physical Signage | Overdue
Client Delivery |  | Instant Message | N/A
Marketing |  | Letter
Projects |  | Social Media
CMT |  | Intranet
Supply Chain |  | Extranet
Data Protection |  | Other